## Cover
Operational ISMS Dashboard
Official Companion Artifact
Abstract
This example is the operational ISMS dashboard for the Arcfield / Arcfield Platform freeze. It shows how the ISMS is running: SoA implementation and evidence, approved mandatory documents, untreated high risks, metrics below target, open CARs, open incidents and improvements, last management review, next internal audit and certificate validity. The next-audit preview is the same 9.2 engine as the internal audit report on this freeze; it is not a recertification decision. KPIs are derived from the 11 September 2026 freeze; this workbook is not a second SoA. It belongs to the surveillance cycle after certificate ARC-ISMS-2025-001.
Document Control
Artifact ID | IMPL-WB
Asset type | Dashboard
Volume | 1
Version | 1.1
Classification | Internal
Owner | ISMS Manager
Approver | Top Management
Effective Date | 2026-09-01
Next Review Date | 2027-09-01
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Legal
Legal Disclaimer
This companion artifact is provided for implementation support and does not constitute legal advice. Validate all controls, evidence and records against your organisation, scope, risk context and applicable requirements.
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Instructions
Instructions
Use the workbook to track implementation status, not to replace the underlying evidence artifacts.
Keep every sheet tied to an owner, source artifact, output and review cadence.
Update readiness metrics with evidence references.
Convert gaps into owned actions with priority and target date.
Review dashboard status before internal audit, management review and certification milestones.
Keep lookup values aligned with current artifact standards.
Use sheets ending in “Ex” as read-only examples. Enter live data only on the matching “Wk” (Working) sheets.
Every operative list is an Excel Table with frozen headers and filters. Add new rows on the next empty worksheet row beneath the table so Excel expands it — do not leave blank rows inside the table.
Where a column offers a dropdown, choose a value from the list (Status, Owner role, Priority, Severity, Likelihood, Impact, Applicability, Evidence Status, Review Result). Do not invent free-text variants.
Enter dates as YYYY-MM-DD. Date columns are validated and formatted accordingly.
Review the Flag columns (Overdue, Review Due, Missing Owner, Missing Evidence). They calculate automatically and highlight gaps for follow-up.
Keep Cover, Legal, Book, Lists and Metadata unchanged. System sheets are protected on purpose.
Open the Dashboard sheet for automatic KPIs and charts driven by Working-table formulas — do not type KPI values by hand.
Use the Traceability sheet to confirm Risk → Treatment → Control → SoA → Evidence → Action ID columns are present and populated.
💡 Hint: Keep the workbook evidence-linked: status without owner, evidence and next action is not audit-ready. Book reference: Implementation & Certification, Implementation Readiness & Planning

## Dashboard
Operational ISMS Dashboard
Formulas over freeze slices in this workbook. Status is colour-coded. Next-best action follows Status; it is a hint, not a work order. Next-audit preview uses the same 9.2 engine as the internal audit report.
KPI | Actual | Of | Status | Next-best action
Status
SoA implemented / applicable
SoA evidence complete / recorded
Mandatory documents approved
MME metrics below target |  | 0
Attention
High risks without treatment ID |  | 0
Open CARs |  | 0
Open incidents |  | 0
Open improvements |  | 0
Cadence
Last management review
Next internal audit
Certificate valid until
Next internal audit preview
Next-audit verdict
Preview major nonconformities |  | 0
Preview minor nonconformities |  | 0
Preview ISMS evidence
Preview ISMS effectiveness

## Packs (hidden)
Clause | Title | Records | Present | Complete
4 | Context of the organization | OS, ISS | 2/2 | Yes
5 | Leadership | ISP | 1/1 | Yes
6 | Planning | RAM, REQT | 2/2 | Yes
7 | Support | DCP, MDR | 2/2 | Yes
8 | Operation | ICP, IRPROC | 2/2 | Yes
9 | Performance evaluation | IAP, MRMT | 2/2 | Yes
10 | Improvement | NC-RP | 1/1 | Yes

## Members (hidden)
Artifact ID | Title | Present
27003-27004-MAP | ISO 27003 / 27004 Conformance Matrix | Yes
ACM | Access Control Matrix | Yes
AI | Asset Inventory | Yes
AISGF | AI System Governance File | Yes
AMP | Asset Management Policy | Yes
AOAVC | Asset Owner Asset Validation Checklist | Yes
AORVC | Asset Owner Risk Validation Checklist | Yes
ARA | Access Request and Approval | Yes
ARR | Access Rights Register | Yes
ASTR | Application Security Testing Register | Yes
AUD-ER | Auditor Evidence Request Log | Yes
BCP | Business Continuity Plan | Yes
BCPOL | Business Continuity Policy | Yes
BIA | Business Impact Analysis (BIA) | Yes
BRP | Backup and Restore Plan | Yes
BRPROC | Backup & Recovery Procedure | Yes
BRT-R | Backup Restore Test Record | Yes
C5-CM | BSI C5 Criteria Mapping | Yes
CAR | Corrective Actions Register | Yes
CB-SEL | Certification Body Selection and Evaluation | Yes
CE-SA | UK Cyber Essentials Self-Assessment | Yes
CERT-DR | Certification Audit Dry-Run Workbook | Yes
CERT-P | Certification Project Plan | Yes
CFE-X | Cross-Framework Evidence Crosswalk | Yes
CICD-H | CI/CD Security Hardening Assessment | Yes
CIL | Continual Improvement Log | Yes
CKMP | Cryptographic Key Management Policy | Yes
CLD-BL | Cloud Security Baseline Assessment | Yes
CMP | Change Management Procedure | Yes
CMTP | Competence Matrix and Training Plan | Yes
CNI | Companion Navigation Index | Yes
COMM-P | ISMS Communication Plan | Yes
CP | Cryptography Policy | Yes
CR | Context Register | Yes
CRA-PSF | Cyber Resilience Act Product Security File | Yes
CSP | Cloud Security Policy | Yes
CSR | Critical Services Register | Yes
CSRM | Cloud Shared Responsibility Matrix | Yes
CSS | Cloud Security Statement | Yes
CSSAQ | Critical Supplier Security Assessment Questionnaire | Yes
DAL | Decision and Action Log | Yes
DCP | Document Control Procedure | Yes
DEP-RISK | Dependency Risk Assessment | Yes
DOP | Documented Operating Procedure | Yes
DPAR | Data Processing Activities Register (GDPR) | Yes
DPIA | Data Protection Impact Assessment | Yes
DPR | Data Processors Register (GDPR) | Yes
DR | Document Register | Yes
DRP | Disaster Recovery Plan (DRP) | Yes
DSAR | Data Subject Access Request | Yes
ELAI | Evidence Log / Audit Pack Index | Yes
ENS-CAT | ENS Categorization | Yes
ENS-MI | ENS Measure-to-Evidence Index | Yes
ENV-LOG | Environmental Monitoring and Alert Log | Yes
EP | Evacuation Plan | Yes
ERR | Executive Risk Report | Yes
EVAC-DR | Evacuation Drill Record | Yes
EXR | Exceptions Register | Yes
FAC-RV | Facility Access Review Assessment | Yes
FDB | Framework Delta Backlog | Yes
FMI | Framework Mapping Index | Yes
GBDR | GDPR Breach Documentation Record | Yes
GS | Gap Statement | Yes
HRP | Human Resources Policy | Yes
HRSP | Human Resources Security Policy | Yes
IAP | Internal Audit Plan | Yes
IAPC | Internal Audit Program & Checklist | Yes
IAS | Information Asset Standard | Yes
ICL | ISMS Communication Log | Yes
ICP | Information Classification Policy | Yes
ICVC | ISO 27001 Control Owner Control Validation Checklist | Yes
IGC | ISMS Governance Calendar | Yes
IL | Incident Log | Yes
IMP | Incident Management Policy | Yes
IMPL-P | Phased ISMS Implementation Plan | Yes
IMPL-WB | ISMS Implementation Workbook | Yes
IPR | Interested Parties Register | Yes
IR-RB | Incident Response Runbooks | Yes
IRAR | ISMS Role Appointment Record | Yes
IRP | Incident Response Policy | Yes
IRPROC | Incident Response Procedure | Yes
IRRT | Incident Register and Reporting | Yes
ISMS-CL | ISMS Change Log | Yes
ISO | Information Security Objectives | Yes
ISOCL | ISO 27001:2022 Clauses | Yes
ISOCTRL | ISO 27001:2022 Controls | Yes
ISP | Information Security Policy | Yes
ISS | ISMS Scope Statement | Yes
ITG-MM | BSI IT-Grundschutz Module Mapping | Yes
KEY-R | Cryptographic Key Register | Yes
LMP | Logging and Monitoring Policy | Yes
LRR | Legal, Regulatory and Contractual Requirements Register | Yes
MDR | Mandatory Documents and Records Register | Yes
MFAR | Multi-Framework Assurance Report | Yes
MME | Monitoring and Measurement Evidence | Yes
MRART | Management Review Agenda & Report | Yes
MRMT | Management Review Minutes | Yes
NC-RP | Nonconformity Response and Corrective Action Pack | Yes
NFR-R | Network Firewall Rule Review Register | Yes
NIS2-RD | NIS2 First-Hours Reporting Drill | Yes
NSP | Network Security Policy | Yes
OBL-CAL | Compliance Obligations Calendar | Yes
OER | Operations Evidence Register | Yes
OFC | Offboarding Checklist | Yes
ONC | Onboarding Checklist | Yes
OPC | Operational Planning and Control Evidence | Yes
OPI | Operational Procedures Index | Yes
OS | Organization Statement | Yes
PAP | Password & Authentication Policy | Yes
PAR | Physical Access Register | Yes
PARR | Policy Approval and Review Register | Yes
PBIVC | Process Owner Business Impact Validation Checklist | Yes
PCI-CDE | PCI DSS CDE Scope and Control Matrix | Yes
PESP | Physical and Environmental Security Policy | Yes
RACI | ISMS RACI Matrix | Yes
RAE | Resource Allocation Evidence | Yes
RAM | Risk Assessment Methodology | Yes
RAMT | Risk Acceptance Minutes | Yes
RASM | Risk Analysis Statement according to Magerit and ISO 27005 | Yes
RCIA | Regulatory Change Impact Assessment | Yes
REL-GATE | Security Release Gate Record | Yes
REQT | ISO 27001 Clauses 4-10 Requirements Tracker | Yes
RMP | Risk Management Plan | Yes
ROAR | ISMS Risks and Opportunities Register | Yes
RPIT | Response Procedure by Incident Type | Yes
RR | Risk Register | Yes
RRS | Records Retention Schedule | Yes
RTP | Risk Treatment Plan | Yes
S1-RDY | Stage 1 Readiness Assessment | Yes
S2-RDY | Stage 2 Readiness and Sampling Assessment | Yes
SAS | Systems Architecture Statement | Yes
SBOM-R | SBOM and Component Inventory | Yes
SCR-C | Secure Code Review Assessment | Yes
SEC-REQ | Security Requirements Register | Yes
SECR | Secrets Management Register | Yes
SI | Software Inventory | Yes
SICT | Security Incident Communication | Yes
SINV | Supplier Inventory | Yes
SIR | Security Incident Register | Yes
SOA | Statement of Applicability (SoA) | Yes
SOAVC | Control Owner Statement of Applicability Validation Checklist | Yes
SOC2-EC | SOC 2 Evidence Calendar | Yes
SOC2-SD | SOC 2 System Description | Yes
SRP | Supplier Relationships Policy | Yes
SSAQ | Supplier Security Assessment Questionnaire | Yes
SSDLC | S-SDLC Implementation Requirements Checklist | Yes
SSDP | Secure Software Development Policy | Yes
STD-SUP | Current Standard Supplement | Yes
TISAX-AS | TISAX Assessment Scope and ISA Mapping | Yes
TMM | Threat Modeling Worksheet | Yes
TR | Training Register | Yes
TRC | Training Records | Yes
UAI | Users and Access Inventory | Yes
VULN-SLA | Vulnerability Remediation SLA Matrix | Yes
WIR-S1 | Work Instruction Record — Security Cycle 1 | Yes
XFA-R | Cross-Framework Applicability | Yes

## ClauseLinks (hidden)
Clause ID | Linked ID | InSnapshot
4.1 | OS | Yes
4.1 | GS | Yes
4.1 | ERR | Yes
4.2 | ERR | Yes
4.2 | SRP | Yes
4.2 | SOC2-SD | Yes
4.3 | ISS | Yes
4.3 | SAS | Yes
4.3 | SINV | Yes
4.4 | GS | Yes
4.4 | WIR-S1 | Yes
4.4 | MRART | Yes
4.4 | MRMT | Yes
5.1 | ISP | Yes
5.1 | MRMT | Yes
5.1 | GS | Yes
5.2 | ISP | Yes
5.2 | TRC | Yes
5.3 | RACI | Yes
5.3 | GS | Yes
5.3 | OS | Yes
6.1.1 | RR | Yes
6.1.1 | RTP | Yes
6.1.1 | RAMT | Yes
6.1.2 | RAM | Yes
6.1.2 | RAMT | Yes
6.1.2 | RASM | Yes
6.1.2 | RR | Yes
6.1.3 | RTP | Yes
6.1.3 | SOA | Yes
6.1.3 | ISOCTRL | Yes
6.2 | ISP | Yes
6.2 | IMPL-WB | Yes
6.2 | MRMT | Yes
6.3 | CMP | Yes
6.3 | CR | Yes
6.3 | ISMS-CL | Yes
7.1 | MRART | Yes
7.1 | MRMT | Yes
7.1 | GS | Yes
7.2 | CMTP | Yes
7.2 | TR | Yes
7.2 | TRC | Yes
7.2 | HRP | Yes
7.3 | TRC | Yes
7.3 | HRSP | Yes
7.4 | COMM-P | Yes
7.4 | SICT | Yes
7.4 | IRP | Yes
7.5 | DCP | Yes
7.5 | DR | Yes
7.5 | WIR-S1 | Yes
8.1 | WIR-S1 | Yes
8.1 | CMP | Yes
8.1 | ISOCTRL | Yes
8.2 | RR | Yes
8.2 | RAM | Yes
8.2 | ISMS-CL | Yes
8.3 | RTP | Yes
8.3 | SOA | Yes
8.3 | CAR | Yes
9.1 | MME | Yes
9.1 | IMPL-WB | Yes
9.1 | MRART | Yes
9.2 | IAP | Yes
9.2 | CAR | Yes
9.2 | MRMT | Yes
9.3 | MRART | Yes
9.3 | MRMT | Yes
10.1 | CIL | Yes
10.1 | CAR | Yes
10.1 | WIR-S1 | Yes
10.2 | CAR | Yes
10.2 | IAP | Yes
10.2 | MRMT | Yes

## ClauseStatus
Clause ID | Implementation status | Evidence status | Linked artifact(s)
4.1 | Implemented | Complete | OS; GS; ERR
4.2 | Implemented | Complete | ERR; SRP; SOC2-SD
4.3 | Implemented | Complete | ISS; SAS; SINV
4.4 | Implemented | Complete | GS; WIR-S1; MRART; MRMT
5.1 | Implemented | Complete | ISP; MRMT; GS
5.2 | Implemented | Complete | ISP; TRC
5.3 | Implemented | Complete | RACI; GS; OS
6.1.1 | Implemented | Complete | RR; RTP; RAMT
6.1.2 | Implemented | Complete | RAM; RAMT; RASM; RR
6.1.3 | Implemented | Complete | RTP; SOA; ISOCTRL
6.2 | Implemented | Partial | ISP; IMPL-WB; MRMT
6.3 | Implemented | Complete | CMP; CR; ISMS-CL
7.1 | Implemented | Partial | MRART; MRMT; GS
7.2 | Implemented | Complete | CMTP; TR; TRC; HRP
7.3 | Implemented | Complete | TRC; HRSP
7.4 | Implemented | Complete | COMM-P; SICT; IRP
7.5 | Implemented | Complete | DCP; DR; WIR-S1
8.1 | Implemented | Complete | WIR-S1; CMP; ISOCTRL
8.2 | Implemented | Complete | RR; RAM; ISMS-CL
8.3 | In progress | Partial | RTP; SOA; CAR
9.1 | Implemented | Partial | MME; IMPL-WB; MRART
9.2 | Implemented | Complete | IAP; CAR; MRMT
9.3 | Implemented | Complete | MRART; MRMT
10.1 | Implemented | Partial | CIL; CAR; WIR-S1
10.2 | Implemented | Complete | CAR; IAP; MRMT

## SoA
Control ID | Applicability | Implementation status | Evidence status
A.5.1 | Applicable | Implemented | Complete
A.5.2 | Applicable | Implemented | Complete
A.5.3 | Applicable | In progress | Partial
A.5.4 | Applicable | Implemented | Complete
A.5.5 | Applicable | Implemented | Partial
A.5.6 | Applicable | Implemented | Partial
A.5.7 | Applicable | In progress | Partial
A.5.8 | Applicable | Implemented | Partial
A.5.9 | Applicable | Implemented | Complete
A.5.10 | Applicable | Implemented | Complete
A.5.11 | Applicable | Implemented | Complete
A.5.12 | Applicable | Implemented | Complete
A.5.13 | Applicable | Implemented | Partial
A.5.14 | Applicable | Implemented | Partial
A.5.15 | Applicable | Implemented | Partial
A.5.16 | Applicable | Implemented | Partial
A.5.17 | Applicable | Implemented | Partial
A.5.18 | Applicable | Implemented | Partial
A.5.19 | Applicable | In progress | Partial
A.5.20 | Applicable | In progress | Partial
A.5.21 | Applicable | Planned | Partial
A.5.22 | Applicable | In progress | Partial
A.5.23 | Applicable | In progress | Partial
A.5.24 | Applicable | Implemented | Complete
A.5.25 | Applicable | Implemented | Partial
A.5.26 | Applicable | Implemented | Partial
A.5.27 | Applicable | Planned | Partial
A.5.28 | Applicable | Implemented | Complete
A.5.29 | Applicable | Implemented | Partial
A.5.30 | Applicable | In progress | Partial
A.5.31 | Applicable | Implemented | Partial
A.5.32 | Applicable | Planned | Partial
A.5.33 | Applicable | Implemented | Complete
A.5.34 | Applicable | Implemented | Partial
A.5.35 | Applicable | Implemented | Complete
A.5.36 | Applicable | Implemented | Partial
A.5.37 | Applicable | In progress | Partial
A.6.1 | Applicable | Implemented | Partial
A.6.2 | Applicable | Implemented | Complete
A.6.3 | Applicable | Implemented | Complete
A.6.4 | Applicable | Planned | Partial
A.6.5 | Applicable | Implemented | Complete
A.6.6 | Applicable | Implemented | Partial
A.6.7 | Applicable | Implemented | Partial
A.6.8 | Applicable | Implemented | Partial
A.7.1 | Applicable | Implemented | Partial
A.7.2 | Applicable | Implemented | Partial
A.7.3 | Applicable | Implemented | Partial
A.7.4 | Applicable | In progress | Partial
A.7.5 | Applicable | Planned | Partial
A.7.6 | Not applicable | Not applicable | Not applicable
A.7.7 | Applicable | Implemented | Partial
A.7.8 | Applicable | Implemented | Partial
A.7.9 | Applicable | Implemented | Partial
A.7.10 | Applicable | Implemented | Partial
A.7.11 | Not applicable | Not applicable | Not applicable
A.7.12 | Not applicable | Not applicable | Not applicable
A.7.13 | Applicable | Implemented | Partial
A.7.14 | Applicable | Implemented | Partial
A.8.1 | Applicable | Implemented | Partial
A.8.2 | Applicable | In progress | Partial
A.8.3 | Applicable | Implemented | Partial
A.8.4 | Applicable | Implemented | Partial
A.8.5 | Applicable | Implemented | Complete
A.8.6 | Applicable | Planned | Partial
A.8.7 | Applicable | Implemented | Partial
A.8.8 | Applicable | In progress | Partial
A.8.9 | Applicable | In progress | Partial
A.8.10 | Applicable | In progress | Partial
A.8.11 | Applicable | Planned | Missing
A.8.12 | Applicable | Planned | Partial
A.8.13 | Applicable | Implemented | Complete
A.8.14 | Applicable | Implemented | Partial
A.8.15 | Applicable | Implemented | Partial
A.8.16 | Applicable | In progress | Partial
A.8.17 | Applicable | Implemented | Partial
A.8.18 | Applicable | In progress | Partial
A.8.19 | Applicable | Implemented | Partial
A.8.20 | Applicable | Implemented | Partial
A.8.21 | Applicable | Implemented | Partial
A.8.22 | Applicable | In progress | Partial
A.8.23 | Applicable | Planned | Missing
A.8.24 | Applicable | Implemented | Complete
A.8.25 | Applicable | Implemented | Partial
A.8.26 | Applicable | In progress | Partial
A.8.27 | Applicable | Planned | Partial
A.8.28 | Applicable | Implemented | Partial
A.8.29 | Applicable | In progress | Partial
A.8.30 | Not applicable | Not applicable | Not applicable
A.8.31 | Applicable | Implemented | Partial
A.8.32 | Applicable | Implemented | Partial
A.8.33 | Applicable | Planned | Missing
A.8.34 | Applicable | Implemented | Partial

## Mandatory
Record ID | Status
MDR-001 | Approved
MDR-002 | Approved
MDR-003 | Update in progress
MDR-004 | Active
MDR-005 | Approved
MDR-006 | Active
MDR-007 | Active
MDR-008 | Approved
MDR-009 | Active
MDR-010 | Approved
MDR-011 | Active
MDR-012 | Draft
MDR-013 | Planned
MDR-014 | Planned
MDR-015 | Approved
MDR-016 | Active
MDR-017 | Active
MDR-018 | Active
MDR-019 | Approved
MDR-020 | Approved
MDR-021 | Active
MDR-022 | Active
MDR-023 | Active
MDR-024 | Approved
MDR-025 | Active
MDR-026 | Active
MDR-027 | Active

## HighRisk
Risk ID | Inherent rating | Treatment ID | Status
RISK-2026-014 | High | RTP-2026-014 | In treatment
RISK-2026-018 | Medium | RTP-2026-018 | In treatment
RISK-2026-021 | Medium | RTP-2026-021 | Open
RISK-2026-027 | High | RTP-2026-027 | In treatment
RISK-2026-031 | Medium | RTP-2026-031 | In treatment
RISK-2026-033 | Medium | RTP-2026-033 | Open
RISK-2026-041 | High | RTP-2026-041 | In treatment
RISK-2026-042 | High | RTP-2026-042 | In treatment
RISK-2026-043 | High | RTP-2026-043 | In treatment
RISK-2026-044 | High | RTP-2026-044 | In treatment
RISK-2026-045 | High | RTP-2026-045 | In treatment
RISK-2026-046 | High | RTP-2026-046 | In treatment

## MME
Metric ID | Metric | Target | Actual Result | Status | Owner | Evidence Reference | Notes
MME-001 | Security awareness completion rate | >= 98% within 30 days | 96% | Below target | HR Manager | TR-2026-Q3 | Related to EXR-005 closure.
MME-002 | Privileged access review completion | 100% critical systems reviewed monthly | 4 of 5 systems reviewed | Below target | IT Operations Manager | ARR-2026-08 | Cloud admin exception open.
MME-003 | High-risk treatment overdue count | 0 overdue high-risk treatments | 1 overdue | Below target | Compliance Lead | RTP-2026-Q3 | Management review input required.
MME-004 | Incident closure within SLA | >= 90% medium/high incidents closed within SLA | 83% | Below target | Incident Manager | IL-REVIEW-2026-08 | One supplier incident open.
MME-005 | Evidence pack completeness | >= 95% complete before freeze | 91% | In progress | Internal Auditor | ELAI-2026-Q3 | ICL-006 freeze notice sent.
MME-006 | Critical supplier assurance evidence current | 100% current evidence for critical suppliers | 5 of 6 suppliers current | In progress | Supplier Manager | SINV-CLOUDHOST-2026-Q3 | Contract addendum pending.

## OpenActions
Action ID | Source | Gap | Related Area | Owner | Priority | Target Date | Evidence Reference | Status
CAR-001 | CAR | Audit evidence for privileged access review was incomplete for two production systems. | Clause 9.2 | IT Operations Manager | Minor nonconformity | 2026-09-15 | CAR-001-ACC-REV | In progress
CAR-003 | CAR | Competence evidence for two control owners was outdated. | Clause 7.2 | HR Manager | Minor nonconformity | 2026-08-25 | CAR-003-CMTP | Effectiveness check
CAR-004 | CAR | One critical supplier agreement lacked explicit breach-notification timing. | A.5.20 | Supplier Manager | Improvement | 2026-09-30 | CAR-004-SUP | In progress
CAR-2026-027 | CAR | IL-005: Manual change outside the standard deployment workflow. Internal draft articles were world-readable for 12 minutes. No confirmed Arcfield Platform customer PII exposure. | A.8.9, A.8.32, A.5.15, A.5.37 | Engineering Lead | Minor nonconformity | 2026-10-15 | CHG-POST-2026-0822 | In progress
CIL-001 | CIL | Automate evidence reminders for access reviews. | A.5.18; Clause 9.2 | IT Operations Manager | High | 2026-09-30 | Linked to CAR-001. | In progress
CIL-002 | CIL | Add supplier exit-readiness status to the supplier inventory. | A.5.19; A.5.20 | Supplier Manager | Medium | 2026-10-15 | Prioritize cloud hosting supplier. | Proposed
CIL-004 | CIL | Create a short secure remote-working refresher. | A.6.7 | HR Manager | Low | 2026-12-15 | Combine with annual awareness refresh. | Deferred
CIL-005 | CIL | Introduce data masking for production-like test data. | A.8.11; A.8.33 | Engineering Lead | High | 2026-10-31 | Aligned with SoA planned controls. | In progress
S1-RDY-004 | S1-RDY | IL-005 re-sample and stalled A.5.27 still open | Clause 9.2 | Security Lead |  | 2026-10-31 | GRC-EVID-2026-Q3 | In progress
S1-RDY-005 | S1-RDY | CB visit not yet held | Clause 9.2 / 9.3 | ISMS Manager |  | 2027-04-30 | CB-SEL | Pending review
8.3 | REQT | Close open treatment effectiveness checks. | Information security risk treatment | Risk Manager |  | 2026-10-31 | RTP-OPEN-2026-Q3 | In progress

## Incidents
Incident ID | Reported Date | Severity | Status | Owner | Category
IL-001 | 2026-08-03 | Low | Closed | Incident Manager | Suspicious email
IL-002 | 2026-08-07 | Medium | Closed | Security Lead | Malware detection
IL-003 | 2026-08-11 | Medium | In review | IT Operations Manager | Unauthorized access attempt
IL-004 | 2026-08-18 | Medium | Open | Supplier Manager | Supplier incident
IL-005 | 2026-08-22 | High | Contained | Engineering Lead | Misconfiguration
IL-006 | 2026-08-27 | Low | Closed | HR Manager | Access delay

## Phases (hidden)
Phase ID | Milestone | Status | Current | Planned Finish
PH-01 | Define ISMS scope | In progress | Yes | 2026-09-06
PH-02 | Identify interested parties and context | Planned | No | 2026-09-11
PH-03 | Establish risk method | Planned | No | 2026-09-13
PH-04 | Perform risk assessment | Not started | No | 2026-09-27
PH-05 | Select controls and prepare SoA | Not started | No | 2026-10-04
PH-06 | Implement treatment plan | Not started | No | 2026-10-25
PH-07 | Operate and collect evidence | Not started | No | 2026-11-08
PH-08 | Review readiness | Not started | No | 2026-11-22

## Cadence
Field | Value
Last management review | 2026-08-29
Next management review | 2026-12-15
Certificate valid until | 2028-04-24
First surveillance | April 2026
Certificate ID | ARC-ISMS-2025-001

## AuditDates
Audit Area | Planned Date | Status
ISMS governance | 2026-09-10 | In progress
Risk management | 2026-09-12 | Planned
Access control | 2026-09-16 | Planned
Supplier management | 2026-09-18 | Planned

## AuditPreview (hidden)
Field | Value
Verdict | certified ISMS; surveillance findings remain
Report ID | IA-ARCFIELD-EN-2026-09-11
Major nonconformities | 11
Minor nonconformities | 93
Findings | 32
Document completeness | High
Document content quality | High
Document consistency | High
ISMS implementation | Low
ISMS evidence | Low
ISMS effectiveness | Low
Note | Same 9.2 engine as the internal audit report on this freeze. Not a recertification decision.

## AuditFindings
Source | Criterion | Score | What
Clause 4, Clause 5, Clause 6, Clause 8 | ISMS implementation | Medium | Organisation-specific process description, but little sign that it is running.
Clause 4, Clause 6, Clause 7, Clause 8 | ISMS effectiveness | Low | This record cannot, on its own, indicate that the ISMS is effective (ISO 27001 9.1 / ISO 27004).
Clause 5, Clause 8 | ISMS evidence | Medium | Evidence pointers exist, but they are not a full operating sample (ISO 27001 9.1, indirect).
Clause 5 | ISMS effectiveness | Medium | Some performance language is present; not enough to conclude the ISMS is effective.
Clause 9 | ISMS implementation | Medium | Implementation impression from 'Status' (ISO 27001 8.1, indirect).
Clause 9 | ISMS effectiveness | Medium | Audit results exist; they indicate evaluation, not yet ISMS effectiveness (ISO 27001 9.1/9.2).
Clause 10 | ISMS implementation | Medium | Implementation impression from 'Closure status' (ISO 27001 8.1, indirect).
Clause 10 | ISMS effectiveness | Medium | Corrective-action effectiveness is recorded in part (ISO 27001 10.1 e).
AI, RAM, RR, RTP, RAMT, BIA, SOA | ISMS effectiveness | Low | This record cannot, on its own, indicate that the ISMS is effective (ISO 27001 9.1 / ISO 27004).
SAS, RAM, BIA | ISMS implementation | Medium | Organisation-specific process description, but little sign that it is running.
SAS | ISMS effectiveness | Medium | Some performance language is present; not enough to conclude the ISMS is effective.
RTP | ISMS implementation | Medium | Implementation impression from 'Status' (ISO 27001 8.1, indirect).
SOA | ISMS implementation | Medium | Implementation impression from 'Implementation status' (ISO 27001 8.1, indirect).
A.5.1, A.5.2, A.5.4, A.5.9, A.5.10, A.5.11, A.5.12, A.5.24, A.5.28, A.5.33, A.5.35 | ISMS effectiveness | Medium | Implemented with complete file evidence; that is still an indirect indication, not proof of ISMS effectiveness (ISO 27001 9.1).
A.5.3, A.5.7, A.5.19, A.5.20, A.5.22, A.5.23, A.5.30, A.5.37 | ISMS implementation | Medium | ISOCTRL/SoA implementation status: In progress.
A.5.3, A.5.5, A.5.6, A.5.7, A.5.8, A.5.13, A.5.14, A.5.15, A.5.16, A.5.17, A.5.18, A.5.19, A.5.20, A.5.21, A.5.22, A.5.23, A.5.25, A.5.26, A.5.27, A.5.29, A.5.30, A.5.31, A.5.32, A.5.34, A.5.36, A.5.37 | ISMS evidence | Medium | Evidence status: Partial.
A.5.3, A.5.5, A.5.6, A.5.7, A.5.8, A.5.13, A.5.14, A.5.15, A.5.16, A.5.17, A.5.18, A.5.19, A.5.20, A.5.21, A.5.22, A.5.23, A.5.25, A.5.26, A.5.27, A.5.29, A.5.30, A.5.31, A.5.32, A.5.34, A.5.36, A.5.37 | ISMS effectiveness | Low | This control row cannot indicate that the ISMS is effective.
A.5.21, A.5.27, A.5.32 | ISMS implementation | Low | ISOCTRL/SoA implementation status: Planned.
A.6.1, A.6.4, A.6.6, A.6.7, A.6.8 | ISMS evidence | Medium | Evidence status: Partial.
A.6.1, A.6.4, A.6.6, A.6.7, A.6.8 | ISMS effectiveness | Low | This control row cannot indicate that the ISMS is effective.
A.6.2, A.6.3, A.6.5 | ISMS effectiveness | Medium | Implemented with complete file evidence; that is still an indirect indication, not proof of ISMS effectiveness (ISO 27001 9.1).
A.6.4 | ISMS implementation | Low | ISOCTRL/SoA implementation status: Planned.
A.7.1, A.7.2, A.7.3, A.7.4, A.7.5, A.7.7, A.7.8, A.7.9, A.7.10, A.7.13, A.7.14 | ISMS evidence | Medium | Evidence status: Partial.
A.7.1, A.7.2, A.7.3, A.7.4, A.7.5, A.7.7, A.7.8, A.7.9, A.7.10, A.7.13, A.7.14 | ISMS effectiveness | Low | This control row cannot indicate that the ISMS is effective.
A.7.4 | ISMS implementation | Medium | ISOCTRL/SoA implementation status: In progress.
A.7.5 | ISMS implementation | Low | ISOCTRL/SoA implementation status: Planned.
A.8.1, A.8.2, A.8.3, A.8.4, A.8.6, A.8.7, A.8.8, A.8.9, A.8.10, A.8.12, A.8.14, A.8.15, A.8.16, A.8.17, A.8.18, A.8.19, A.8.20, A.8.21, A.8.22, A.8.25, A.8.26, A.8.27, A.8.28, A.8.29, A.8.31, A.8.32, A.8.34 | ISMS evidence | Medium | Evidence status: Partial.
A.8.1, A.8.2, A.8.3, A.8.4, A.8.6, A.8.7, A.8.8, A.8.9, A.8.10, A.8.11, A.8.12, A.8.14, A.8.15, A.8.16, A.8.17, A.8.18, A.8.19, A.8.20, A.8.21, A.8.22, A.8.23, A.8.25, A.8.26, A.8.27, A.8.28, A.8.29, A.8.31, A.8.32, A.8.33, A.8.34 | ISMS effectiveness | Low | This control row cannot indicate that the ISMS is effective.
A.8.2, A.8.8, A.8.9, A.8.10, A.8.16, A.8.18, A.8.22, A.8.26, A.8.29 | ISMS implementation | Medium | ISOCTRL/SoA implementation status: In progress.
A.8.5, A.8.13, A.8.24 | ISMS effectiveness | Medium | Implemented with complete file evidence; that is still an indirect indication, not proof of ISMS effectiveness (ISO 27001 9.1).
A.8.6, A.8.11, A.8.12, A.8.23, A.8.27, A.8.33 | ISMS implementation | Low | ISOCTRL/SoA implementation status: Planned.
A.8.11, A.8.23, A.8.33 | ISMS evidence | Low | Evidence status: Missing.

## Review and decision
Review and decision
Field | Value
Decision | KPI values are Excel formulas over measure slices loaded from the evidence snapshot. This workbook does not store a separate readiness percentage.
Workbook sections reviewed | 7
Metrics reviewed | 6
Open gaps | 11
Next milestone | 2026-09-12
Reviewed by | ISMS Manager
Decision date | 2026-08-29
Evidence reference | arcfield.platform.surv.2026-09-11
💡 Hint: Close with a decision so implementation readiness and remaining blockers are explicit. Book reference: Implementation & Certification, Implementation Readiness & Planning

## References
References
Cite these sources from workshops and audits. This list names ISO clauses, book chapters and companion artifacts used by this file.
[ISO/IEC 27001:2022](https://www.iso.org/standard/82875.html) — Normative source this artifact implements or cites.
[Implementation & Certification, Implementation Readiness & Planning](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Primary operating chapter for this companion artifact.
[Implementation & Certification, Implementation Readiness & Planning](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Primary operating chapter for this companion artifact.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Documented information, review and version discipline.
[DCP Document Control Procedure (Secure Engineering, Access Control & Identity Management)](https://www.amazon.com/dp/9789908983455) — Interface record. Cite this Document Control version; do not copy this file into that record.
[ELAI Evidence Log / Audit Pack Index (Implementation & Certification, Audit Process)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[MDR Mandatory Documents and Records Register (Implementation & Certification, Asset Management & Information Classification)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[REQT ISO 27001 Clauses 4-10 Requirements Tracker (Dual Compliance, ISO 27001 & NIS2)](https://www.amazon.com/dp/9789908983479) — Interface record. Cite this Document Control version; do not copy this file into that record.

## Traceability
Traceability — IMPL-WB
Chain Step | Expected ID Column | Found On Sheet | Sample Header | Rows With ID | Orphan Risk
Risk | risk_id | HighRisk | Risk ID |  | OK
Treatment | treatment_id | HighRisk | Treatment ID |  | OK
Control | control_id | SoA | Control ID |  | OK
SoA | soa_id | — | — | 0 | Missing column
Evidence | evidence_id | ClauseStatus | Evidence status |  | OK
Action | action_id | OpenActions | Action ID |  | OK
Chain: Risk → Treatment → Control → SoA → Evidence → Action

## Metadata (hidden)
key | value
brand | ExportableProof
issuer | MessemerTech
brandRelationship | ExportableProof is an imprint of MessemerTech.
packageId | iso27001-software-companies-volume-1-en-basic-companion
packageVersion | 1.0.97
artifactId | IMPL-WB
artifactTitle | Operational ISMS Dashboard
assetType | Dashboard
recommendedFormat | XLSX
bookVolume | 1
bookTitle
language | en
tier | Basic
releaseDate
sourceChapter | CURATED-076
sourceHeading | ISMS Implementation Workbook
generatedRunId | create_inventory.curated_companion.20260919T152623Z

## _Payload (hidden)
{{payload_title}}
{{payload}}

## _Content (hidden)
{{section_title}}
{{body_text}}
💡 Hint: {{hint}}