## Cover
Risk Treatment Plan
Official Companion Artifact
Abstract
This example links Arcfield risk treatment decisions to concrete treatment actions, Annex A controls, SoA linkage, owners, approvals, target dates, evidence, residual-risk decisions and effectiveness checks. Rows are the 11 September 2026 operating sample of the certified Arcfield Platform ISMS in the surveillance cycle after certificate ARC-ISMS-2025-001.
Document Control
Artifact ID | RTP
Asset type | Register
Volume | 1
Version | 1.1
Classification | Internal
Owner | Risk Manager
Approver | Top Management
Effective Date | 2026-09-01
Next Review Date | 2027-09-01
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Legal
Legal Disclaimer
This companion artifact is provided for implementation support and does not constitute legal advice. Validate all controls, evidence and records against your organisation, scope, risk context and applicable requirements.
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Instructions
Instructions
Create one treatment row for every risk that requires mitigation, avoidance, transfer, or explicit acceptance.
Link each treatment to a Risk Register row and, where relevant, Annex A controls and the SoA.
Assign a role-based action owner and approving risk owner.
Record target date, status, completion evidence, and effectiveness check.
Recalculate or confirm residual risk after treatment.
Escalate overdue high-risk treatment actions to management review.
Use sheets ending in “Ex” as read-only examples. Enter live data only on the matching “Wk” (Working) sheets.
Every operative list is an Excel Table with frozen headers and filters. Add new rows on the next empty worksheet row beneath the table so Excel expands it — do not leave blank rows inside the table.
Where a column offers a dropdown, choose a value from the list (Status, Owner role, Priority, Severity, Likelihood, Impact, Applicability, Evidence Status, Review Result). Do not invent free-text variants.
Enter dates as YYYY-MM-DD. Date columns are validated and formatted accordingly.
Review the Flag columns (Overdue, Review Due, Missing Owner, Missing Evidence). They calculate automatically and highlight gaps for follow-up.
Keep Cover, Legal, Book, Lists and Metadata unchanged. System sheets are protected on purpose.
Reuse Risk IDs from the Risk Register on every treatment row; record SoA linkage and Action owner from the role dropdown.
💡 Hint: Treatment entries should reuse the same risk IDs and asset/control references from the Risk Register. Book reference: Building the ISMS, Planning, Risk & Objectives (Clause 6)

## Register schema (hidden)
Register schema
Column | Type | Required | Description | Example
Treatment ID | text | yes | Stable unique treatment identifier. | RTP-2026-014
Related risk ID | text | yes | Linked Risk Register entry. | RISK-2026-014
Risk title | text | yes | Short risk title. | Unauthorized privileged access to production platform
Treatment option | select | yes | Mitigate, Avoid, Transfer, Accept. | Mitigate
Treatment action | text | yes | Action required to treat the risk. | Implement quarterly privileged-access review evidence pack
Annex A control(s) | text | conditional | Related ISO controls. | A.5.15, A.5.16, A.8.2
SoA linkage | text | conditional | Linked SoA control rows. | SOA-A.5.15
Action owner | text | yes | Role responsible for implementation. | IT Operations
Risk owner approval | text | yes | Risk owner decision or approval status. | Approved by Service Owner
Start date | date | yes | Treatment start date. | 2026-08-29
Target date | date | yes | Planned completion date. | 2026-09-30
Completion date | date | conditional | Actual completion date. | 2026-09-28
Status | select | yes | Planned, In progress, Implemented, Accepted, Closed, Overdue. | In progress
Evidence of completion | text | conditional | Evidence of implemented treatment. | ACC-REV-2026-Q3
Residual risk ID | text | conditional | Residual-risk reference. | RISK-2026-014-R
Residual risk decision | text | conditional | Acceptance or further treatment decision. | Residual risk accepted as Medium
Effectiveness check | text | conditional | How effectiveness will be or was checked. | Q4 privileged access review confirms no unauthorized admin accounts
Review date | date | yes | Last review date. | 2026-08-29
Notes | text | no | Additional context. | Evidence pack due before management review.
💡 Hint: The schema must prove action ownership, control linkage, completion evidence, residual-risk decision, and effectiveness verification. Book reference: Building the ISMS, Planning, Risk & Objectives (Clause 6)

## Treatment plan entries Ex
Treatment ID | Related risk ID | Risk title | Treatment option | Treatment action | Annex A control(s) | SoA linkage | Action owner | Risk owner approval | Start date | Target date | Completion date | Status | Evidence of completion | Residual risk ID | Residual risk decision | Effectiveness check | Review date | Notes | Flag: Overdue | Flag: Review Due | Flag: Missing Owner
RTP-2026-014 | RISK-2026-014 | Unauthorized privileged access to production platform | Mitigate | Implement quarterly privileged-access review evidence pack | A.5.15, A.5.16, A.8.2 | SOA-A.5.15 | IT Operations | Approved by Service Owner | 2026-08-29 | 2026-09-30 |  | In progress | ACC-REV-2026-Q3 pending | RISK-2026-014-R | Residual risk expected Medium | Q4 review confirms privileged access baseline | 2026-08-29 | Must close before management review.
RTP-2026-018 | RISK-2026-018 | Customer Portal outage affects onboarding commitments | Transfer / Mitigate | Confirm SaaS SLA, escalation route, and exit support | A.5.19, A.5.20, A.5.23, A.8.14 | SOA-A.5.23 | Supplier Manager | Approved by Head of Customer Success | 2026-08-29 | 2026-10-15 |  | In progress | SINV-CLOUDHOST-2026-Q3 | RISK-2026-018-R | Residual risk expected Medium | Supplier SLA reviewed during Q4 supplier review | 2026-08-29 | Supplier contact update pending.
RTP-2026-021 | RISK-2026-021 | ISMS evidence repository loses integrity | Mitigate | Implement quarterly export and permission review for evidence repository | A.5.33, A.8.13 | SOA-A.5.33 | Workspace Administrator | Approved by ISMS Manager | 2026-08-28 | 2026-09-15 |  | Planned | EVID-EXPORT-2026-Q3 planned | RISK-2026-021-R | Residual risk expected Low | Restore test and permission sample | 2026-08-28 | Align with audit-pack generation. STALL-2026-Q3: this treatment has not moved since the 2025 improvement programme.
RTP-2026-027 | RISK-2026-027 | Source repository secret exposure | Mitigate | Validate secret scanning and branch protection for customer portal repository | A.8.4, A.8.5, A.8.28 | SOA-A.8.28 | DevOps Engineer | Approved by Engineering Lead | 2026-08-27 | 2026-09-20 |  | In progress | SSDLC-REL-2026-014 | RISK-2026-027-R | Residual risk expected Medium | Release evidence includes scan results | 2026-08-27 | Link to S-SDLC evidence.
RTP-2026-031 | RISK-2026-031 | Identity provider misconfiguration | Mitigate | Add monthly identity-provider configuration and break-glass review | A.5.15, A.5.17, A.8.2 | SOA-A.5.17 | IT Operations | Approved by IT Operations Manager | 2026-08-29 | 2026-09-30 |  | In progress | IAM-CTRL-2026-Q3 | RISK-2026-031-R | Residual risk expected Low | Next monthly configuration sample | 2026-08-29 | Privileged review cadence required.
RTP-2026-033 | RISK-2026-033 | HR personnel data retained beyond requirement | Mitigate | Execute the treatment recorded on RISK-2026-033 and keep evidence on the cited control records. | A.5.31, A.5.34, A.8.10 | SOA-A.5.34 | HR Manager | Approved by HR Manager | 2026-09-11 | 2026-11-20 |  | Planned | RTP-2026-033 evidence pending | RISK-2026-033-R | Residual risk expected Low | Next review confirms residual rating | 2026-09-11 | Link retention schedule to folder review. STALL-2026-Q3: this treatment has not moved since the 2025 improvement programme.
RTP-2026-041 | RISK-2026-041 | Customer health records exposed from misconfigured object storage | Mitigate | Execute the treatment recorded on RISK-2026-041 and keep evidence on the cited control records. | A.5.12, A.5.33, A.8.3 | SOA-A.5.33 | Cloud Service Owner | Approved by Cloud Service Owner | 2026-09-11 | 2026-12-11 |  | In progress | RTP-2026-041 evidence pending | RISK-2026-041-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Linked to ICP Restricted handling and CSP shared-responsibility split.
RTP-2026-042 | RISK-2026-042 | Unreviewed CI/CD change reaches Arcfield Platform production | Mitigate | Execute the treatment recorded on RISK-2026-042 and keep evidence on the cited control records. | A.8.25, A.8.28, A.8.32 | SOA-A.8.28 | Engineering Lead | Approved by Engineering Lead | 2026-09-11 | 2026-10-31 |  | In progress | RTP-2026-042 evidence pending | RISK-2026-042-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Cite SSDP and the production change record; do not copy pipeline YAML into RR.
RTP-2026-043 | RISK-2026-043 | Hosting supplier cannot evidence the shared-responsibility split | Mitigate | Execute the treatment recorded on RISK-2026-043 and keep evidence on the cited control records. | A.5.19, A.5.21, A.5.23 | SOA-A.5.19 | Supplier Manager | Approved by Supplier Manager | 2026-09-11 | 2026-11-30 |  | In progress | RTP-2026-043 evidence pending | RISK-2026-043-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Linked to SRP and CSP. Exit clause follow-up is ISO-006.
RTP-2026-044 | RISK-2026-044 | Privileged cloud-console session without recording | Mitigate | Execute the treatment recorded on RISK-2026-044 and keep evidence on the cited control records. | A.8.2, A.8.5, A.8.15 | SOA-A.8.2 | IT Operations Manager | Approved by IT Operations Manager | 2026-09-11 | 2026-10-31 |  | In progress | RTP-2026-044 evidence pending | RISK-2026-044-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Complements RISK-2026-014. Evidence is the PAM session export, not this row.
RTP-2026-045 | RISK-2026-045 | Arcfield Platform backup restore untested for customer configuration | Mitigate | Execute the treatment recorded on RISK-2026-045 and keep evidence on the cited control records. | A.5.29, A.5.30, A.8.13 | SOA-A.8.13 | Operations Lead | Approved by Operations Lead | 2026-09-11 | 2026-12-11 |  | In progress | RTP-2026-045 evidence pending | RISK-2026-045-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Cite BRP restore evidence. Linked to BCP/BIA recovery objectives.
RTP-2026-046 | RISK-2026-046 | Support attachment with health data copied into an unapproved SaaS tool | Mitigate | Execute the treatment recorded on RISK-2026-046 and keep evidence on the cited control records. | A.5.10, A.5.12, A.8.12 | SOA-A.5.10 | Incident Manager | Approved by Incident Manager | 2026-09-11 | 2026-10-31 |  | In progress | RTP-2026-046 evidence pending | RISK-2026-046-R | Residual risk expected Medium | Next review confirms residual rating | 2026-09-11 | Linked to ICP handling rules and DSAR/DPIA records. Do not paste attachments into RR.
Formulas:
Flag: Review Due = IF(AND([Review date]<>"",[Review date]<=TODAY()+30,[Review date]>=TODAY()),"Yes","")

## Treatment plan entries Wk
Treatment ID | Related risk ID | Risk title | Treatment option | Treatment action | Annex A control(s) | SoA linkage | Action owner | Risk owner approval | Start date | Target date | Completion date | Status | Evidence of completion | Residual risk ID | Residual risk decision | Effectiveness check | Review date | Notes | Flag: Overdue | Flag: Review Due | Flag: Missing Owner
Formulas:
Flag: Review Due = IF(AND([Review date]<>"",[Review date]<=TODAY()+30,[Review date]>=TODAY()),"Yes","")

## Register completeness decision
Register completeness decision
Field | Value | Evidence reference | Evidence status
Completeness result | Complete | RTP-COMPLETE-2026-Q3 | Complete
Reviewed by | Risk Manager | RTP-COMPLETE-2026-Q3 | Complete
Risks requiring treatment | 5 | RTP-COMPLETE-2026-Q3 | Complete
Treatments without owner | 0 | RTP-COMPLETE-2026-Q3 | Complete
Treatments without target date | 0 | RTP-COMPLETE-2026-Q3 | Complete
Treatments without risk owner approval | 0 | RTP-COMPLETE-2026-Q3 | Complete
Implemented treatments without evidence | 0 | RTP-COMPLETE-2026-Q3 | Complete
Overdue high-risk treatments | 0 | RTP-COMPLETE-2026-Q3 | Complete
Final status | Audit-ready | RTP-COMPLETE-2026-Q3 | Complete
Decision date | 2026-08-29 | RTP-COMPLETE-2026-Q3 | Complete
Evidence reference | RTP-COMPLETE-2026-Q3 | RTP-COMPLETE-2026-Q3 | Complete
💡 Hint: The completeness decision should identify whether any treatment action blocks audit readiness. Book reference: Building the ISMS, Planning, Risk & Objectives (Clause 6)

## Evidence and records
Evidence and records
Related records live in the companion documents named below. This file cites them by their approved version. It does not copy their content. The Owner named on the cover is accountable for those live records.
[Risk Register](RR_Risk_Register.xlsx) — Live Risk IDs this plan treats.
[Risk Acceptance Minutes](RAMT_Risk_Acceptance_Minutes.docx) — Residual decisions after treatment.
[Statement of Applicability](SOA_Statement_of_Applicability_SoA.xlsx) — Annex A controls named on treatment rows.

## References
References
Cite these sources from workshops and audits. This list names ISO clauses, book chapters and companion artifacts used by this file.
[ISO/IEC 27001:2022](https://www.iso.org/standard/82875.html) — Normative source this artifact implements or cites.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Information Security Policies & Risk Management](https://www.amazon.com/dp/9789908983448) — Policy framework and risk-based operation.
[SOA Statement of Applicability (SoA) (Building the ISMS, Context of the Organization (Clause 4))](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.
[ISO Information Security Objectives (Building the ISMS, Information Security Policies & Risk Management)](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.
[RR Risk Register (Building the ISMS, Planning, Risk & Objectives (Clause 6))](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.
[SINV Supplier Inventory (Building the ISMS, Supplier Security & Third-party Risk Management)](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.

## Traceability
Traceability — RTP
Chain Step | Expected ID Column | Found On Sheet | Sample Header | Rows With ID | Orphan Risk
Risk | risk_id | Treatment plan entries Wk | Related risk ID |  | OK
Treatment | treatment_id | Treatment plan entries Wk | Treatment ID |  | OK
Control | control_id | Treatment plan entries Wk | Annex A control(s) |  | OK
SoA | soa_id | Treatment plan entries Wk | SoA linkage |  | OK
Evidence | evidence_id | Treatment plan entries Wk | Evidence of completion |  | OK
Action | action_id | Treatment plan entries Wk | Treatment action |  | OK
Chain: Risk → Treatment → Control → SoA → Evidence → Action

## Lists (hidden)
domain.owner | domain.status.generic
ISMS Manager | Draft
Control Owner | In Progress
Risk Owner | Under Review
Process Owner | Approved
Asset Owner | Closed
IT Security | Deferred
HR
Legal
Executive Management
Internal Audit

## Metadata (hidden)
key | value
brand | ExportableProof
issuer | MessemerTech
brandRelationship | ExportableProof is an imprint of MessemerTech.
packageId | iso27001-software-companies-volume-1-en-basic-companion
packageVersion | 1.0.97
artifactId | RTP
artifactTitle | Risk Treatment Plan
assetType | Register
recommendedFormat | XLSX
bookVolume | 1
bookTitle
language | en
tier | Basic
releaseDate
sourceChapter | CURATED-128
sourceHeading | Risk Treatment Plan
generatedRunId | create_inventory.curated_companion.20260919T152623Z

## _Payload (hidden)
{{payload_title}}
{{payload}}

## _Content (hidden)
{{section_title}}
{{body_text}}
💡 Hint: {{hint}}