## Cover
Operational Planning and Control Evidence
Official Companion Artifact
Abstract
This example demonstrates Arcfield operational planning and control for recurring ISMS activities, including criteria, owners, evidence, results, deviations, follow-up actions and review decisions. Rows are the 11 September 2026 operating sample of the certified Arcfield Platform ISMS in the surveillance cycle after certificate ARC-ISMS-2025-001.
Document Control
Artifact ID | OPC
Asset type | Register
Volume | 1
Version | 1.1
Classification | Internal
Owner | ISMS Manager
Approver | Top Management
Effective Date | 2026-09-01
Next Review Date | 2027-09-01
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Legal
Legal Disclaimer
This companion artifact is provided for implementation support and does not constitute legal advice. Validate all controls, evidence and records against your organisation, scope, risk context and applicable requirements.
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Instructions
Instructions
Identify recurring or event-driven ISMS operational activities.
Define the applicable criteria, frequency and accountable owner.
Record evidence produced by each activity.
Capture deviations, issues and follow-up actions.
Link evidence references and next due dates.
Review open deviations before management review.
Use sheets ending in “Ex” as read-only examples. Enter live data only on the matching “Wk” (Working) sheets.
Every operative list is an Excel Table with frozen headers and filters. Add new rows on the next empty worksheet row beneath the table so Excel expands it — do not leave blank rows inside the table.
Where a column offers a dropdown, choose a value from the list (Status, Owner role, Priority, Severity, Likelihood, Impact, Applicability, Evidence Status, Review Result). Do not invent free-text variants.
Enter dates as YYYY-MM-DD. Date columns are validated and formatted accordingly.
Review the Flag columns (Overdue, Review Due, Missing Owner, Missing Evidence). They calculate automatically and highlight gaps for follow-up.
Keep Cover, Legal, Book, Lists and Metadata unchanged. System sheets are protected on purpose.
💡 Hint: Record recurring ISMS operations with defined criteria, evidence expectations and escalation routes for deviations. Book reference: Building the ISMS, Planning, Risk & Objectives (Clause 6)

## Operational control register Ex
Control Activity ID | Operational Activity | Related Clause or Control | Planned Frequency | Control Criteria | Owner | Evidence Produced | Last Performed Date | Result | Deviation or Issue | Follow-up Action | Next Due Date | Evidence Reference | Status | Notes | Flag: Overdue | Flag: Missing Owner | Flag: Missing Evidence
OPC-001 | Monthly privileged access review | A.8.2 | Monthly | All privileged accounts for critical systems are reviewed by system owners. | IT Operations Manager | Access Review Register update | 2026-08-28 | Partially completed | Cloud admin review pending | Complete cloud admin review and close EXR-001 | 2026-09-05 | ARR-2026-08 | Open follow-up | Management visibility required.
OPC-002 | Supplier assurance evidence review | A.5.19-A.5.23 | Quarterly | Critical suppliers have current security evidence and contractual commitments. | Supplier Manager | Supplier inventory and assessment update | 2026-08-15 | Partially completed | CloudHost notification addendum pending | Track addendum through LRR and EXR | 2026-09-10 | SINV-CLOUDHOST-2026-Q3 | Open follow-up | Related to LRR-005.
OPC-003 | Incident log review | A.5.24-A.5.28 | Weekly for open incidents | Open incidents have owner, status, evidence and closure plan. | Incident Manager | Incident review decision | 2026-08-29 | Completed | Supplier final report pending | Follow up with Supplier Manager | 2026-09-06 | IL-REVIEW-2026-08 | In progress | One supplier incident remains open.
OPC-004 | Evidence pack completeness review | Clause 7.5 and Clause 9.2 | Monthly during audit preparation | Evidence records have owner, status, source and review date. | Internal Auditor | Evidence Log / Audit Pack Index | 2026-08-29 | In progress | Two evidence records need confirmation | Confirm ELAI-004 and ELAI-006 before freeze | 2026-09-05 | ELAI-2026-Q3 | In progress | ICL freeze notice sent.
OPC-005 | Security awareness completion review | Clause 7.2 and A.6.3 | Monthly | Training completion rate reaches target and late completion is followed up. | HR Manager | Training report and reminder log | 2026-08-29 | Below target | Two contractor acknowledgements pending | Send reminder and report completion in MME | 2026-09-03 | TR-2026-Q3 | Open follow-up | Related to ISO-001.
OPC-006 | Change impact review for ISMS changes | Clause 6.3 and Clause 8.1 | Per ISMS change | ISMS changes have reason, consequences, owner, approval and effectiveness review. | ISMS Manager | ISMS Change Log entry | 2026-08-29 | Completed | Effectiveness reviews pending for open changes | Review in next management review | 2026-11-12 | ISMS-CL-REVIEW-2026-Q3 | Active | Scope change under implementation.

## Operational control register Wk
Control Activity ID | Operational Activity | Related Clause or Control | Planned Frequency | Control Criteria | Owner | Evidence Produced | Last Performed Date | Result | Deviation or Issue | Follow-up Action | Next Due Date | Evidence Reference | Status | Notes | Flag: Overdue | Flag: Missing Owner | Flag: Missing Evidence

## Operational review decision
Operational review decision
Field | Value
Review result | Six operational activities reviewed; four have follow-up actions and no uncontrolled deviation was accepted.
Activities reviewed | 6
Activities on schedule | 2
Deviations open | 4
Follow-up actions open | 4
Reviewed by | ISMS Manager
Decision date | 2026-08-29
Evidence reference | OPC-REVIEW-2026-08
💡 Hint: Close with a review decision so operational deviations feed corrective action and management review. Book reference: Building the ISMS, Planning, Risk & Objectives (Clause 6)

## References
References
Cite these sources from workshops and audits. This list names ISO clauses, book chapters and companion artifacts used by this file.
[ISO/IEC 27001:2022 8.1](https://www.iso.org/standard/82875.html) — Normative source this artifact implements or cites.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Information Security Policies & Risk Management](https://www.amazon.com/dp/9789908983448) — Policy framework and risk-based operation.
[ELAI Evidence Log / Audit Pack Index (Implementation & Certification, Audit Process)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[ISO Information Security Objectives (Building the ISMS, Information Security Policies & Risk Management)](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.
[EXR Exceptions Register (Implementation & Certification, Asset Management & Information Classification)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[LRR Legal, Regulatory and Contractual Requirements Register (Building the ISMS, Legal, Regulatory & Contractual Requirements)](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.

## Lists (hidden)
domain.owner | domain.status.generic
ISMS Manager | Draft
Control Owner | In Progress
Risk Owner | Under Review
Process Owner | Approved
Asset Owner | Closed
IT Security | Deferred
HR
Legal
Executive Management
Internal Audit

## Metadata (hidden)
key | value
brand | ExportableProof
issuer | MessemerTech
brandRelationship | ExportableProof is an imprint of MessemerTech.
packageId | iso27001-software-companies-volume-1-en-premium-companion
packageVersion | 1.0.97
artifactId | OPC
artifactTitle | Operational Planning and Control Evidence
assetType | Register
recommendedFormat | XLSX
bookVolume | 1
bookTitle
language | en
tier | Premium
releaseDate
sourceChapter | CURATED-106
sourceHeading | Operational Planning and Control Evidence
generatedRunId | create_inventory.curated_companion.20260919T152623Z

## _Payload (hidden)
{{payload_title}}
{{payload}}

## _Content (hidden)
{{section_title}}
{{body_text}}
💡 Hint: {{hint}}