## Cover
Resource Allocation Evidence
Official Companion Artifact
Abstract
This example evidences Arcfield ISMS resource allocation decisions, including resource needs, related activities, owners, approvals, allocated resources, planned and actual dates, status and evidence references. Rows are the 11 September 2026 operating sample of the certified Arcfield Platform ISMS in the surveillance cycle after certificate ARC-ISMS-2025-001.
Document Control
Artifact ID | RAE
Asset type | Register
Volume | 1
Version | 1.1
Classification | Internal
Owner | ISMS Manager
Approver | Top Management
Effective Date | 2026-09-01
Next Review Date | 2027-09-01
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Legal
Legal Disclaimer
This companion artifact is provided for implementation support and does not constitute legal advice. Validate all controls, evidence and records against your organisation, scope, risk context and applicable requirements.
© 2026. MessemerTech OÜ. ExportableProof is an imprint of MessemerTech. All rights reserved.

## Instructions
Instructions
Record resource needs that affect ISMS implementation or operation.
Link each need to an ISMS activity, objective, risk treatment or evidence requirement.
Capture requested owner, approval role, decision and allocated resource.
Track planned and actual dates.
Link evidence of approval, allocation or review.
Escalate blocked or under-resourced items before management review.
Use sheets ending in “Ex” as read-only examples. Enter live data only on the matching “Wk” (Working) sheets.
Every operative list is an Excel Table with frozen headers and filters. Add new rows on the next empty worksheet row beneath the table so Excel expands it — do not leave blank rows inside the table.
Where a column offers a dropdown, choose a value from the list (Status, Owner role, Priority, Severity, Likelihood, Impact, Applicability, Evidence Status, Review Result). Do not invent free-text variants.
Enter dates as YYYY-MM-DD. Date columns are validated and formatted accordingly.
Review the Flag columns (Overdue, Review Due, Missing Owner, Missing Evidence). They calculate automatically and highlight gaps for follow-up.
Keep Cover, Legal, Book, Lists and Metadata unchanged. System sheets are protected on purpose.
💡 Hint: Record resource decisions with enough evidence to show that implementation constraints were managed. Book reference: Building the ISMS, Support & Resources (Clause 7)

## Resource allocation register Ex
Resource ID | Resource Need | Related ISMS Activity | Resource Type | Owner | Requested By | Approval Role | Decision | Allocated Resource | Planned Date | Actual Date | Evidence Reference | Status | Notes | Flag: Missing Owner | Flag: Missing Evidence
RAE-001 | ISMS implementation coordination capacity | Phased implementation plan | People | ISMS Manager | Compliance Lead | Top Management | Approved | 0.5 FTE ISMS Manager for 12 weeks | 2026-09-02 | 2026-09-02 | IMPL-P-REVIEW-2026-W35 | Allocated | Supports scope, risk and evidence phases.
RAE-002 | Access review automation pilot | Privileged access review | Tooling | Security Lead | IT Operations Manager | ISMS Manager | Approved | Security engineer plus integration sandbox | 2026-10-01 |  | ELAI-AUTO-2026-PILOT | Planned | Related to ISMS-CHG-002.
RAE-003 | Supplier evidence review support | Critical supplier assurance | People | Supplier Manager | Compliance Lead | COO | Approved | Supplier Manager and Legal Counsel review slot | 2026-09-10 |  | SINV-CLOUDHOST-2026-Q3 | In progress | CloudHost addendum pending.
RAE-004 | Internal audit readiness review | Internal audit programme | People | Internal Auditor | ISMS Manager | Top Management | Approved | Two-day internal audit window | 2026-11-11 |  | IAP-PLAN-2026-Q4 | Planned | Evidence freeze required first.
RAE-005 | Incident response tabletop exercise | Incident handling improvement | People and time | Incident Manager | Security Lead | ISMS Manager | Approved | Two-hour cross-functional tabletop session | 2026-09-25 |  | IRRT-REVIEW-2026-08 | Scheduled | Supplier incident scenario planned.
RAE-006 | Data masking remediation effort | Secure development and privacy review | Engineering capacity | Engineering Lead | Privacy Lead | CTO | Approved with priority review | One sprint story plus privacy review checkpoint | 2026-09-10 |  | EXR-004 | Open | Linked to ISMS-CHG-005.

## Resource allocation register Wk
Resource ID | Resource Need | Related ISMS Activity | Resource Type | Owner | Requested By | Approval Role | Decision | Allocated Resource | Planned Date | Actual Date | Evidence Reference | Status | Notes | Flag: Missing Owner | Flag: Missing Evidence

## Resource review decision
Resource review decision
Field | Value
Review result | Resource allocations are sufficient for the current implementation phase; one remediation item remains open.
Resource items reviewed | 6
Approved items | 6
Open items | 4
Blocked items | 0
Reviewed by | ISMS Manager
Decision date | 2026-08-29
Evidence reference | RAE-REVIEW-2026-Q3
💡 Hint: Close with a review decision so resource gaps are visible before they affect certification readiness. Book reference: Building the ISMS, Support & Resources (Clause 7)

## References
References
Cite these sources from workshops and audits. This list names ISO clauses, book chapters and companion artifacts used by this file.
[ISO/IEC 27001:2022 7.1](https://www.iso.org/standard/82875.html) — Normative source this artifact implements or cites.
[Building the ISMS, Support & Resources (Clause 7)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Support & Resources (Clause 7)](https://www.amazon.com/dp/9789908983448) — Primary operating chapter for this companion artifact.
[Building the ISMS, Planning, Risk & Objectives (Clause 6)](https://www.amazon.com/dp/9789908983448) — Documented information, review and version discipline.
[ISO Information Security Objectives (Building the ISMS, Information Security Policies & Risk Management)](https://www.amazon.com/dp/9789908983448) — Interface record. Cite this Document Control version; do not copy this file into that record.
[ELAI Evidence Log / Audit Pack Index (Implementation & Certification, Audit Process)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[EXR Exceptions Register (Implementation & Certification, Asset Management & Information Classification)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.
[IAP Internal Audit Plan (Implementation & Certification, Internal Audit & Management Review)](https://www.amazon.com/s?k=ISO+27001+for+Software+Companies+Implementation+and+Certification) — Interface record. Cite this Document Control version; do not copy this file into that record.

## Lists (hidden)
domain.owner | domain.status.generic
ISMS Manager | Draft
Control Owner | In Progress
Risk Owner | Under Review
Process Owner | Approved
Asset Owner | Closed
IT Security | Deferred
HR
Legal
Executive Management
Internal Audit

## Metadata (hidden)
key | value
brand | ExportableProof
issuer | MessemerTech
brandRelationship | ExportableProof is an imprint of MessemerTech.
packageId | iso27001-software-companies-volume-1-en-premium-companion
packageVersion | 1.0.97
artifactId | RAE
artifactTitle | Resource Allocation Evidence
assetType | Register
recommendedFormat | XLSX
bookVolume | 1
bookTitle
language | en
tier | Premium
releaseDate
sourceChapter | CURATED-116
sourceHeading | Resource Allocation Evidence
generatedRunId | create_inventory.curated_companion.20260919T152623Z

## _Payload (hidden)
{{payload_title}}
{{payload}}

## _Content (hidden)
{{section_title}}
{{body_text}}
💡 Hint: {{hint}}